| Project Title | # Adaptive Readout Interface for Wireless Implantable Sensors |
| --- | --- |
| Student | Breandán Gillanders |
| Supervisor | Dr. Adnan Elahi |
| Co-Assessor |  |
| This Revision | Revision 1 |

# Scope Statement

Battery-less implantable LC sensors enable continuous, real-time monitoring of physiological parameters by encoding changes in variables such as pressure or strain into shifts in their resonant frequency. However, long-term performance can be affected by biological factors such as fibrotic tissue encapsulation, which alters coupling conditions, increases losses, and degrades wireless readout accuracy. Maintaining reliable operation under these changing conditions requires adaptive circuitry capable of compensating for varying link efficiency. This project aims to evaluate and improve an existing wireless readout circuit developed for passive implantable sensors. The system interrogates the implanted LC resonator via inductive coupling, measuring the reflection coefficient (S₁₁) to detect shifts in the resonant frequency of the sensor. Building on this foundation, the project will design and integrate a tuneable (reconfigurable) amplifier stage to dynamically adjust gain and stabilise performance as coupling conditions change, ensuring consistent and accurate resonance detection. The scope of the project includes the following: - Literature review on existing techniques for measuring S₁₁ and resonant frequency detection. - Circuit evaluation, schematic review, and performance benchmarking of the current system. - Simulation (LTSpice/QucsStudio) of RF front-end and amplifier stages. - Design, implementation, and tuning of a reconfigurable amplifier for adaptive gain control. - Integration and experimental validation of the improved system. - Evaluation of system stability and resonance tracking accuracy under variable coupling conditions. - Documentation and presentation of design process, results, and future recommendations.

# Stakeholder List

Stakeholder; Power; Interest; Concerns. Supervisor; High; High; Timely achievement of project milestones and solutions to project issues. Regular reporting & achievement of deliverables. Co-Assessor; Medium; Low; Achieve deliverables; clear documentation for assessment; overall project quality and completion. Student (me); High; High; Technical feasibility, meeting project scope and deadlines; demonstrating competency and producing results. Translational Medical Device Lab; High; High; Functional prototype that aligns with their research goals; practical, scalable readout system design; documentation for future development; experimental data. Technical Officers; Medium; Medium; Safe and effective use of lab equipment; availability of components. EEE Department; High; Medium; Compliance with academic standards, successful and innovative project outcome. University of Galway; High; Low; Adherence to institutional research policies and procedures.. End Users; Low; High; Reliability, safety, non-invasiveness, and ultimate improvement in patient care and monitoring.

Table of Contents

Scope Statement	1

Stakeholder List	2

Table of Contents	3

Deliverables	4

Work Breakdown	4

Literature review and design requirements	4

Evaluation and refinement of the current readout circuit	5

Design of reconfigurable amplifier module	5

Reconfigurable readout circuit integration	6

Final Report	6

Work Schedule	7

Task Scheduling Table #1	7

Task Scheduling Table #2	8

Communications Strategy	9

Health & Safety Risk Assessments	10

# Deliverables

Fixed Deliverables These are standard for all projects and should be incorporated into your Work Breakdown and Work Schedules below. - Project Plan (working ‘live’ document) - Progress Presentation (PPT document) - Project Presentation/Poster/Demo - Final Project Report (Word document)

Interim Deliverables - Literature Review - Existing circuit evaluation results - Circuit Simulation Results - Prototype circuits (reconfigurable amplifier circuit) - Final wireless reader system - Testing and validation results of final system

| # Work Breakdown |  |
| --- | --- |
| Work Package #1 | ## Literature review and design requirements |
| Task #1 | Review the underlying theory of resonant sensing systems. |
| Task #2 | Perform a literature review on magnetic-resonant bioelectronic implants for cardiovascular monitoring, with emphasis on their readout circuitry. Additionally, review current techniques and circuit implementations for measuring reflection (S₁₁) and transmission (S₂₁) coefficients relevant to these systems. |
| Task #3 | Investigate reconfigurable and programmable amplifier designs. Define design requirements for this application (e.g. operating frequency range, max transmitted power level etc.) |
| Linked Deliverables |  |
| Expected Outputs | Literature review and design requirements |

| Work Package #2 | ## Evaluation and refinement of the current readout circuit |
| --- | --- |
| Task #1 | Review circuit schematics, PCB design and layout, and simulation models of current circuit design. Isolate and test each subsystem individually (DDS, phase shifter, phase detector, filters etc.) before performing full-system evaluation. |
| Task #2 | Perform complete system testing after individual subsystem verification. Benchmark overall performance and compare with design expectations. |
| Task #3 | Incorporate design improvements to the circuit as informed by system testing results and additional insights obtained from the literature review. |
| Linked Deliverables |  |
| Expected Outputs | Existing circuit benchmark results and improved version |

| Work Package #3 | ## Design of reconfigurable amplifier module |
| --- | --- |
| Task #1 | Design the reconfigurable amplifier architecture based on design requirements (gain range, bandwidth etc.). Perform LTSpice simulations of the design to evaluate functionality and component selection. |
| Task #2 | Translate the simulated design into a PCB using Altium/KiCad, ensuring RF design best practices are adhered to. Fabricate the PCB in the TMD lab. Solder components to PCB. |
| Task #3 | Test the amplifier using a signal generator and an oscilloscope. Record metrics on the gain and phase response of the amplifier. Compare measured data with simulated results. |
| Linked Deliverables |  |
| Expected Outputs | Validated amplifier design, PCB prototype board |

| Work Package #4 | ## Reconfigurable readout circuit integration |
| --- | --- |
| Task #1 | Integrate the reconfigurable amplifier module with the improved readout system to evaluate system-level performance and identify requirements for merging all components onto a single PCB. Update the firmware and implement a FreeRTOS-based framework to manage concurrent tasks, including communication with the DDS, ADC, and data processing. |
| Task #2 | Develop a new PCB layout incorporating lessons learned from the existing device. Export Gerber files, BOM. Ensure components are readily available in the lab or can be easily sourced. Submit the finalized PCB design for fabrication. Procure all necessary components and assemble the revised board within the lab. |
| Task #3 | Conduct validation and performance testing of the fully integrated PCB, comparing measured results with expected results and benchmarking the final system in terms of accuracy and reproducibility. |
| Linked Deliverables |  |
| Expected Outputs | Integrated PCB design and updated firmware |

| Work Package #5 | ## Final Report |
| --- | --- |
| Task #1 | Document the full system, detailing the circuit and PCB design, firmware implementation, and experimental results obtained at each stage of testing. |
| Task #2 | Identify limitations in the circuit design, determine areas for improvement, and compile a list of recommendations for the next design revision. |
| Task #3 | Prepare the final project report and presentation, summarising the design process, results, and key findings. Incorporate the literature review, system documentation and suggestions for future work. |
| Linked Deliverables |  |
| Expected Outputs | Final system testing results |

# Work Schedule

| ## Task Scheduling Table #1 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| WP # | Task # | Dependencies | Start Date | End Date | Deliverable | Notes |
| WP1 |  | n/a | 13/10/2025 | 17/11/2025 |  |  |
|  | T1 | n/a | 13/10/2025 | 22/10/2025 |  |  |
|  | T2 | n/a | 22/10/2025 | 31/10/2025 | Literature Review |  |
|  | T3 | n/a | 03/11/2025 | 17/11/2025 |  |  |
| WP2 |  |  | 22/10/2025 | 01/12/2025 |  |  |
|  | T1 |  | 22/10/2025 | 31/10/2025 |  |  |
|  | T2 |  | 03/11/2025 | 17/11/2025 | Benchmarking Results |  |
|  | T3 |  | 17/11/2025 | 01/12/2025 | Circuit Improvements |  |
| WP3 |  |  | 10/11/2025 | 08/12/2025 |  |  |
|  | T1 |  | 10/11/2025 | 24/11/2025 |  |  |
|  | T2 |  | 24/11/2025 | 01/12/2025 |  |  |
|  | T3 |  | 01/12/2025 | 08/12/2025 | Finalised Amplifer Design |  |
| WP4 |  |  | 05/01/2026 | 02/03/2026 |  |  |
|  | T1 |  | 05/01/2026 | 19/01/2026 |  |  |
|  | T2 |  | 19/01/2026 | 16/02/2026 | Wireless Reader System | Dependent on PCB manufacturing time |
|  | T3 |  | 16/02/2026 | 02/03/2026 | Validation Results |  |
| WP5 |  |  | 19/01/2026 | 30/03/2026 |  |  |
|  | T1 |  | 19/01/2026 | 16/02/2026 |  | Can be done in parallel with PCB manufacturing |
|  | T2 |  | 02/03/2026 | 09/03/2026 |  |  |
|  | T3 |  | 09/03/2026 | 30/03/2026 | Project Report |  |

| ## Task Scheduling Table #2 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP # | Task # | Deliv # | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April |
| WP1 |  |  |  |  |  |  |  |  |  |  |
|  | T1 |  |  | XX |  |  |  |  |  |  |
|  | T2 |  |  | XX |  |  |  |  |  |  |
|  | T3 |  |  |  | XX |  |  |  |  |  |
| WP2 |  |  |  |  |  |  |  |  |  |  |
|  | T1 |  |  | XX |  |  |  |  |  |  |
|  | T2 |  |  |  | XX |  |  |  |  |  |
|  | T3 |  |  |  | XX |  |  |  |  |  |
| WP3 |  |  |  |  |  |  |  |  |  |  |
|  | T1 |  |  |  | XX |  |  |  |  |  |
|  | T2 |  |  |  | XX |  |  |  |  |  |
|  | T3 |  |  |  |  | XX |  |  |  |  |
| WP4 |  |  |  |  |  |  |  |  |  |  |
|  | T1 |  |  |  |  |  | XX |  |  |  |
|  | T2 |  |  |  |  |  | XX | XX |  |  |
|  | T3 |  |  |  |  |  |  | XX |  |  |
| WP5 |  |  |  |  |  |  |  |  |  |  |
|  | T1 |  |  |  |  |  | XX | XX |  |  |
|  | T2 |  |  |  |  |  |  |  | X |  |
|  | T3 |  |  |  |  |  |  |  | XXX |  |

# Communications Strategy

Name; Recipient(s); Frequency; Medium; Contents. Status Reports; Supervisor; Weekly (Friday); SharePoint; Bullet-point summary of weekly activities, issues encountered and planned next steps.. Supervisor Meetings; Supervisor; Weekly (Wednesday); In-Person; Discussion of progress, review of challenges, and identification of solutions or required support.. Progress Presentation; Supervisor & Co-Assessor; Once (start of semester 2); In-Person; Presentation summarising progress to date and outlining objectives and timelines for Semester 2.. Poster; All Stakeholders; Once (public event); Poster Session; Presentation summarising progress to date and outlining objectives and timelines for Semester 2.. Final Project Report; Supervisor & Co-Assessor; Once (end of project); PDF Document; Comprehensive final report detailing all project work, results, and conclusions..

# Health & Safety Risk Assessments